## Introduction
Document Control Information
School | Van Lang University
Faculty | Information Technology
Team Name | GSC Team

## Estimate Test
Name: Ngô Trí Cường |  |  |  | Date: | 2015-10-13 |  | Units: Hours
Goal Statement: Estimate time for each task
Task Name | Est 1 | ∆1 | ∆2 | ∆3 | ∆4 | Total | Assumptions
1. Testing | 645
1.0 Test Process | 5
1.1 Test Planning | 640
1.1.1 Test Plan | 8
1.1.1.1 Test strategy | 4
1.1.1.2 Test Schedule | 4
1.1.2 Design Test Case | 242
1.1.2.1 Acceptance Test Specification | 42
1.1.2.1.1. Acceptance Test Specification For User Management Feature | 5
1.1.2.1.2. Acceptance Test Specification For Catalogue Management Feature | 5
1.1.2.1.3. Acceptance Test Specification For Question Management Feature | 5
1.1.2.1.4. Acceptance Test Specification For Setting Management Feature | 5
1.1.2.1.5. Acceptance Test Specification For Executing Management Feature | 22
1.1.2.2 System Test Specification | 168
1.1.2.2.1. System Test Specification For User Management Feature | 10
1.1.2.2.2. System Test Specification For Catalogue Management Feature | 10
1.1.2.2.3. System Test Specification For Question Management Feature | 22
1.1.2.2.4. System Test Specification For Setting Management Feature | 84
1.1.2.2.5. System Test Specification For Executing Management Feature | 42
1.1.2.3 Integration Test Specification | 32
1.1.3 Execute Test Case | 192
1.1.3.1 Execute Test Case For Increment 1 | 76
1.1.3.1.1. Execute System Test Case | 40
1.1.3.1.1.1 Execute System Test Case For User Management Feature | 10
1.1.3.1.1.2 Execute System Test Case For Catalogue Management Feature | 10
1.1.3.1.1.3 Execute System Test Case For Question Management Feature | 20
1.1.3.1.2. Execute Integration Test Case | 18
1.1.3.1.3. Execute Acceptance Test Case | 18
1.1.3.1.3.1 Execute Acceptance Test Case For User Management Feature | 6
1.1.3.1.3.2 Execute Acceptance Test Case For Catalogue Management Feature | 6
1.1.3.1.3.3 Execute Acceptance Test Case For Question Management Feature | 6
1.1.3.2 Execute Test Case For Increment 2 | 116
1.1.3.2.1. Execute System Test Case | 80
1.1.3.2.1.1 Execute System Test Case For Setting Management Feature | 50
1.1.3.2.1.2 Execute System Test Case For Executing Management Feature | 30
1.1.3.2.2. Execute Integration Test Case | 18
1.1.3.2.3. Execute Acceptance Test Case | 18
1.1.3.2.3.1 Execute Acceptance Test Case For Setting Management Feature | 10
1.1.3.2.3.2 Execute Acceptance Test Case For Executing Management Feature | 8
1.1.4 Test Report | 198
1.1.4.1 Report Test Case For Increment 1 | 78
1.1.4.1.1. Report System Test Case | 42
1.1.4.1.1.1 Report System Test Case For User Management Feature | 10
1.1.4.1.1.2 Report System Test Case For Catalogue Management Feature | 10
1.1.4.1.1.3 Report System Test Case For Question Management Feature | 22
1.1.4.1.2. Report Integration Test Case | 18
1.1.4.1.3. Report Acceptance Test Case | 18
1.1.4.1.3.1 Report Acceptance Test Case For Setting Management Feature | 10
1.1.4.1.3.2 Report Acceptance Test Case For Executing Management Feature | 8
1.1.4.2 Report Test Case For Increment 2 | 120
1.1.4.2.1. Report System Test Case | 84
1.1.4.2.1.1 Report System Test Case For Setting Management Feature | 50
1.1.4.2.1.2 Report System Test Case For Executing Management Feature | 34
1.1.4.2.2. Report Integration Test Case | 18
1.1.4.2.3. Report Acceptance Test Case | 18
1.1.4.2.3.1 Report Acceptance Test Case For Setting Management Feature | 10
1.1.4.2.3.2 Report Acceptance Test Case For Executing Management Feature | 8
Total Estimate | 645
THANK YOU FOR YOUR BUSINESS!